## Sheet1
Hardware | Predicted time | Actual time | Status | Real Time | Sim Time
-Setup demo system with CANBus | 4 | 0 | DONE | 0 | 4
C implementation
-Bitwise operations | 1 | 0 | DONE | 0 | 1
Software Setup
Config and Timing | 1 | 1 | DONE | 1 | 1
RTOS
-Create main RTOS implementation | 24 | 24 | DONE | 24 | 24
Interrupts
-Interrupts (Get the interrupts working in conjunction with RTOS) | 2 | 1.5 | DONE | 1.5 | 2
-Enable relevant interrupts | 1 | 0 | DONE | 0 | 1
-Interrupt Priorities | 1 | 0 | DONE |  | 1
Buzzer
-Implement all buzzer signals | 1 | 1 | DONE | 1 | 1
-Buzzer RTOS Task | 1 | 1 | DONE | 1 | 1
-Buzzer coded signal output | 4 |  | WAIT |  | 0
LCD Screen
-Send command to screen | 4 | 4 | DONE | 4 | 4
-Send text to screen | 2 | 2 | DONE | 2 | 2
-Send graphics to screen | 2 | 2 | DONE | 2 | 2
-Implement 53 Column LCD Setup | 4 | 4 | DONE | 4 | 4
-Create Additional Characters | 1.5 | 1.5 | DONE | 1.5 | 1.5
-Add additional Characters to LCD CG space | 2.5 | 2.5 | DONE | 2.5 | 2.5
-Create GUI Notes, Messages, Menus, Panels, Buttons | 8 | 8 | DONE | 8 | 8
-Create graphics library | 4 | 4 | DONE | 4 | 4
-Create Medium and Large size options for the LCD | 3 | 8 | DONE | 8 | 3
-Implement Medium size font | 3 | 8 | DONE | 8 | 3
-Implement large size font | 2 | 8 | DONE | 8 | 2
-Charts | 8 | 14 | DONE | 14 | 8
Buttons
-Detect input signal from all buttons | 1 | 3 | DONE | 3 | 1
-Software debounce | 2 | 0.5 | DONE | 0.5 | 2
-Implement button handler for all buttons | 3 | 1 | DONE | 1 | 3
-Implement buttons on RTOS | 2 | 0 | DONE | 0 | 2
CAN Communication
-Setup CAN registers | 2 | 4 | DONE | 4 | 2
-Message Test | 4 | 16 | DONE | 16 | 4
-Basic Messages Send | 10 | 12 | DONE | 12 | 10
-Basic Messages Receive | 10 | 10 | DONE | 10 | 10
-Flow Rate Management Send | 8 | 5 | DONE | 5 | 8
-Flow Rate Management Receive | 12 | 12 | DONE | 12 | 12
-Easy Calibration | 20 |  | TODO | 20 | 0
Opperating System
-Get system to check if initialised before | 12 | 10.5 | DONE |  | 12
-Initialisation sequence | 6 | 26 | DONE |  | 6
-Planting sequence | 6 | 50 | DONE | 50 | 6
USB PC connection
-FT232 setup | 8 | 6 | DONE | 6 | 8
-Send and receive messages | 8 | 8 | DONE | 8 | 8
-Implement standard messaging system (console) | 8 |  | TODO | 8 | 0
USB Data storage
-FTDI setup | 1 | 2 | DONE | 2 | 1
-Send and receive messages | 1 | 2 | DONE | 2 | 1
-Implement standard messaging system | 1 |  | TODO | 1 | 0
-Boot loader implementation | 20 |  | WAIT | 20 | 0
-Secondary device firmware update | 20 |  | WAIT | 20 | 0
-Transfer precision application rate files | 8 |  | WAIT | 8 | 0
Flash
-Communicate with flash | 2 | 8 | DONE | 8 | 2
-Send data block to flash | 2 | 1 | DONE | 1 | 2
-Read data from flash | 2 | 0 | DONE | 0 | 2
-Create library for flash | 4 |  | TODO | 4 | 0
-Log Files | 8 |  | TODO | 8 | 0
-Copy Log Files | 2 |  | TODO | 2 | 0
-Load Precision application rate files (Up to 20 files) | 4 |  | TODO | 4 | 0
EEPROM
-Communicate with EEPROM | 2 | 2 | DONE | 2 | 2
-Send data to EEPROM | 2 | 2 | DONE | 2 | 2
-Receive data from EEPROM | 2 | 2 | DONE | 2 | 2
-Create library for EEPROM | 4 | 12 | BUSY | 4 | 0
-Update settings with USB | 4 |  | TODO | 4 | 0
-Send settings to USB | 2 |  | TODO | 2 | 0
Humidity Sensor
-Communicate with sensor | 2 | 2 | DONE | 2 | 2
-Send data to sensor | 2 | 2 | DONE | 2 | 2
-Receive data from sensor | 2 | 2 | DONE | 2 | 2
-Create library for sensor | 4 |  | TODO | 4 | 0
GPS
-Communication | 2 | 3 | DONE | 3 | 2
-parse for RMC sentence | 8 | 8 | DONE | 8 | 8
--Get Real Speed | 2 | 0 | DONE | 0 | 2
-Switch between GPS and RS232 | 8 |  | TODO | 8 | 0
GUI
-Intro Screen | 6 | 4 | DONE | 4 | 6
-Setup screen
--Send Config Mode Message (Main Unit) | 1 | 8 | DONE | 8 | 1
--Go into config mode (Secondary unit) | 1 | 8 | DONE | 8 | 1
--Get keypad working (Secondary unit) | 1 | 1 | DONE | 1 | 1
--On-keypress return receive message (Main Unit) | 1 | 1 | DONE | 1 | 1
--Reply with device ID (Main Unit) | 1 | 1 | DONE | 1 | 1
--Mayor's Message (Secondary unit) | 1 | 1 | DONE | 1 | 1
--Register device (Main Unit) | 0.5 | 0.5 | DONE | 0.5 | 0.5
--Register Envelopes (Secondary unit) | 0.5 | 0.5 | DONE | 0.5 | 0.5
--Update Screen (Main Unit) | 0.5 | 0.5 | DONE | 0.5 | 0.5
--Finish Config (Main Unit) | 0.5 | 0.5 | DONE | 0.5 | 0.5
--Tank Screen | 0 | 20 | DONE | 20 | 0
-Planting screen
--Update Flow rate as data is received (Main Unit) | 4 | 4 | DONE | 4 | 4
--Change Active Rows | 4 | 6 | DONE | 6 | 4
-Manual input (settings Screen) | 20 | 25 | DONE | 25 | 20
Variables (Design, implement all the variables and assign memory)
-ImplementTankCapacity | 0.5 | 1 | DONE | 1 | 0.5
-RowsPerHectare | 0.5 | 0 | DONE | 0 | 0.5
-LandNumber | 0.5 | 0 | DONE | 0 | 0.5
-StandardApplicationRate | 0.5 | 0 | DONE | 0 | 0.5
-Implement Variables | 0.5 | 0 | DONE | 0 | 0.5
-Alarm Variables | 0.5 | 0 | DONE | 0 | 0.5
Calculations
-Calculate Flow rate from speed | 1 | 2 | DONE | 2 | 1
-Target Flow Rate | 1 | 1 | DONE | 1 | 1
-ActualRate_kg_per_h | 0.5 | 1 | DONE | 1 | 0.5
-PopulatedSpeed | 0.5 | 1 | DONE | 1 | 0.5
-FertilizerType | 1 | 0 | DONE | 0 | 1
-Radius Planting | 4 |  | TODO | 4 | 0
Signals (Implement handlers for incoming signals)
-Engaged signal control when to dispense liquid | 2 | 14 | DONE | 14 | 2
-Pressure signal | 2 | 8 | DONE | 8 | 2
--Compare pressure against alarms | 2 | 0.5 | DONE | 0.5 | 2
-Tank Level | 2 | 2.5 | DONE | 2.5 | 2
--Compare against minor and major alarms | 2 | 1 | DONE | 1 | 2
Flow Control Unit
Integrate new CANBus code and Flow Control Code | 0 | 24 | DONE | 24 | 0
Communicate with main unit | 0 | 1 | DONE | 1 | 0
Control Flow | 0 | 30 | DONE | 30 | 0
Keypad LED setup | 0 | 4 | DONE | 4 | 0
FC Peripheral Unit
Engage Setup | 0 | 8 | DONE | 8 | 0
Integrate new CANBus code and FC Code | 0 | 0 | DONE | 0 | 0
Administration
-Documentation | 10 | 5 | BUSY | 10 | 0
Design
-Main Unit Function Design | 16 | 8 | BUSY | 16 | 0
Summary | Predicted time | Actual time
Project Total | 416 | 585
Done | 265
To Do | 151